## Task List
Task # | Task Description | Resource | Duration Estimate (days) | Dependencies | Milestone?
1 | Write Project Charter | PM Team | 1 | N/A | No
2 | Create Project Schedule | PM Team | 1 | 1 + 9 days | No
3 | Write Status Report Week 2 | PM Team | 1 | 3 + 10 days | No
4 | Write Status Report Week 4 | PM Team | 1 | 4 + 10 days | No
5 | Write Status Report Week 6 | PM Team | 1 | 5 + 10 days | No
6 | Write Status Report Week 8 | PM Team | 1 | 6 + 10 days | No
7 | Write User Requirements Speficiation | Rhonda Requirements | 3 | 1 | No
8 | Write Functional Requirements Specification | Rhonda Requirements | 2 | 7 | No
9 | Interface Diagram | Rhonda Requirements | 1 | 8 | No
10 | Decide Requirements: Go/No Go | Prisha Pallavi | 0 | 9 | Yes ✩
11 | Develop - Modified Customized Invoice Code | Danny Developer | 2 | 10 | No
12 | Test - Modified Customized Invoice Code | Thomas Tester | 1 | 11 | No
13 | Develop- HR Systems Interface Code | Danny Developer | 2 | 12 | No
14 | Test - HR Systems Interface Code | Thomas Tester | 1 | 13 | No
15 | Develop - Customized Reports | Danny Developer | 2 | 14 | No
16 | Test - Customized Reports | Thomas Tester | 1 | 15 | No
17 | Develop - Audit Log | Danny Developer | 2 | 16 | No
18 | Test- Audit Log | Thomas Tester | 1 | 17 | No
19 | Development Complete: Go/ No Go | Prisha Pallavi | 0 | 18 | Yes ✩
20 | System Test Plan | Thomas Tester | 3 | 19 | No
21 | Write Test Case - Modified Customized Invoice | Thomas Tester | 2 | 20 | No
22 | Execute Test Case- Modified Customized Invoice | Contractor | 1 | 21 | No
23 | Write Test Case - HR Systems Interface | Thomas Tester | 2 | 22 | No
24 | Execute Test Case- HR Systems Interface | Contractor | 1 | 23 | No
25 | Write Test Case - Customized Reports | Thomas Tester | 2 | 24 | No
26 | Execute Test Case - Customized Reports | Contractor | 1 | 25 | No
27 | Write Test Case - Audit Log | Thomas Tester | 2 | 26 | No
28 | Execute Test Case - Audit Log | Contractor | 1 | 27 | No
29 | FAA Validation 1/2 | Contractor | 2 | 28 | No
30 | FAA Validation 2/2 | Thomas Tester | 3 | 29 | No
31 | Write Test Summary Report | Thomas Tester | 2 | 30 | No
32 | Write UAT Plan | Rhonda Requirements | 2 | 31 | No
33 | Write UAT Test Cases | Rhonda Requirements | 2 | 32 | No
34 | UAT Test Execution | Prisha Pallavi | 2 | 33 | No
35 | Test Complete: Go/No Go | Prisha Pallavi | 0 | 34 | Yes ✩
36 | Write Release Notes | Rhonda Requirements | 1 | 35 | No
37 | Write Installation Instructions | Danny Developer | 2 | 36 | No
38 | Train End Users | Rhonda Requirements | 3 | 36 | No
39 | Install Software | Danny Developer | 1 | 38 | No
40 | Customer Acceptance: Go/No Go | Prisha Pallavi | 0 | 39 | Yes ✩